## Sheet1
PPAP Documentation Monitoring Sheet
Customer Name : AKR Engineering Pvt. Ltd. |  | Part . No. : SS 314 TPM 434 |  |  | Drawing / Rev. No : AKR-45-162/v.1.25
Supplier Name : ZZL Eng. Gen Pvt. Ltd |  | Part Name : Automobile Tubing |  |  | Date: 17-04-2012
S. No | Description | Applicability | Submission Level | Status | Document No. / Ref | Responsible Dept. | Remarks
|  | Customer / Supplier | Level 1–5 (as per AIAG PPAP) | Pending / Submitted / Approved
1 | Design Records | Supplier | Level 3 | Submitted | DR-001 | Design Engg. | –
2 | Engineering Change Documents | Supplier | Level 3 | Pending | EC-Rev2 | Engg. | To be updated
3 | Customer Engineering Approval | Customer | Level 3 | Approved | CEA-025 | Customer QA | –
4 | Design FMEA | Supplier | Level 3 | Submitted | DFMEA-01 | Quality | –
5 | Process Flow Diagrams | Supplier | Level 3 | Submitted | PFD-07 | Manufacturing | Minimum Req. from Supplier
6 | Process FMEA | Supplier | Level 3 | Submitted | PFMEA-05 | Quality | –
7 | Dimensional Results | Supplier | Level 3 | Approved | DIM-025 | QC | –
8 | Material & Performance Test Results | Supplier | Level 3 | Pending | MTR-004 | Lab | External lab test required
9 | Initial Process Study | Supplier | Level 3 | Submitted | IPS-02 | Production | –
10 | Measurement System Analysis Studies | Supplier | Level 3 | Approved | MSA-09 | Quality | –
11 | Qualified Laboratory Documentation | Supplier | Level 3 | Submitted | LAB-01 | Lab | –
12 | Control Plan | Supplier | Level 3 | Submitted | CP-07 | Quality | –
13 | Part Submission Warrant (PSW) | Supplier | Level 3 | Pending | PSW-01 | QA | –
14 | Appearance Approval Report (AAR), if applicable | Customer / Supplier | Level 3 | N/A | – | Design | Not applicable
15 | Bulk Material Requirements Checklist | Supplier | Level 3 | Approved | BMR-02 | Purchasing | –
16 | Sample Product | Supplier | Level 3 | Submitted | SPL-05 | Production | –
17 | Master Sample | Supplier | Level 3 | Submitted | MS-01 | QA | –
18 | Checking Aids | Supplier | Level 3 | Pending | CA-01 | Tooling | To be completed
19 | Records of Compliance with Customer Specific Requirement | Supplier | Level 3 | Approved | CSR-02 | QA | –
Prepared By : ___________________ |  | Reviewed By : ___________________ |  |  | Approved By : ___________________

## Disclaimer
Any articles, templates, or information provided by inpaspages.com on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.