## Sheet1
Standard Operating Procedure (SOP) for New Machine Management
GENERAL INFO. |  | Step No. | Activity / Process | Responsibility | Output / Document | Remarks
Document No. : | MFG/DG/BP/03 | 1 | New tool identified as per APQP | Design / R&D | Tool requirement note | Based on project need
Revision No. : | 1 | 2 | Prepare drawing for new machine | R&D Engineer | Machine Drawing | Approval required
Revision Date : | 01.01.20212 | 3 | Preparation of bar chart | Planning Dept. | Bar Chart | Timeline for activity
Effective Date : | 05.01.20212 | 4 | Outsourcing decision | Plant Head / R&D | Decision Record | Yes / No
Department : | Engineering / Production | 5a | If outsourced → Discussion with Plant Incharge, rate finalization & follow-up | Purchase + Plant | Vendor PO / Follow-up report | Ensure vendor qualification
Prepared By : | R&D Engineer | 5b | If in-house → Arrange manufacturing internally | Plant + R&D | Internal Work Order | Use existing resources
Checked By : | QA Head | 6 | Machine inspection as per drawing & trials with QA & PRD | QA + PRD + R&D | Machine Trial Report | Validation
Approved By : | Plant Head | 7 | Tool numbering as per WI | Maintenance / QA | List of Machine | WI followed
|  | 8 | Handover to Production Department | Plant Incharge | Handover Note | Final step
S O P F L O W C H A R T
Prepare drawing for new machine.
Res. Development Engineer
New tool as per APQP.
1. Discussion with Plant Incharge for rates & other issues.
2.Followup of out source activity.
Arrangement of in house mfg.
1.Machine inspection as per drawing.
2. Machine trials with QA & PRD departments.
WI for Machine numbring system
Tool numbring as per work-instructions
Machine drawing
Is out sourced?
No
Yes
Preparation of bar chart
Bar chart
Machine trial report.
Handover Machine to production department.
List of of Machine.
A
A

## Disclaimer
Any articles, templates, or information provided by inpaspages.com on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.