## Sheet1
Non-Conformity Report (NCR) & Corrective / Preventive Action (CAPA)
Company Name / Logo | Division / Department | Report No. | Date
ABC XYZ PVT. LTD | Assembly Line – 2 | NCR/QA/2012/014 | 18-08-2012
Document No. | Revision No. | Issue Date | Page No.
QMS/NCR/05 | 03 | 2012-01-01 | 1 of 1
Part A – Non-Conformity Details
NCR Type | ☐ Process ☐ Product ☐ Audit ☑ Customer Complaint
Non-Conformity Description | Paint peeling observed on 15 pieces during final inspection.
Reference Document | WI/PS/2012/03
Location / Line / Machine ID | Paint Booth – Line 2
Classification of NC | ☐ Critical ☑ Major ☐ Minor
Risk Category | Quality / Customer Complaint
Initiated By | QA Inspector
Reviewed By | Paint Shop Supervisor
Resolved By | QA Head
Immediate Containment Action | Defective lot isolated & tagged
Proposed Disposition Action | ☑ Rework (Repainting)
Supporting Documents | Inspection Report No. QA/FR/325
Time Required | 2 Days
Resolution | Proposal Approved as Proposed
Product Status | ☑ Non-Conformance ☐ Re-Conformance
Part B – Corrective Action
Action(s) Taken to Correct Non-Conformity | Repaint defective pieces under controlled drying.
Responsible Person / Dept. | Paint Shop Supervisor
Resources Needed | Additional drying racks
Proposed Completion Date | 20-08-2012
Reviewed By & Date | QA Head – 20-08-2012
Approved By & Date | Plant Manager – 21-08-2012
Part C – Root Cause Analysis
Method Used | 5-Why
Root Cause Identified | Inadequate drying time before handling.
Contributory Factors | Method / Man
Date of Completion | 20-08-2012
Part D – Preventive / Recurrence Control
Actions Taken | Drying time increased to 30 mins, Operators trained, SOP updated.
Verification Method | Internal Audit / Trial Run
Responsible Person for Monitoring | QA Supervisor
Effectiveness Criteria | Defect rate reduced to <0.5%
Proposed Completion Date | 22-08-2012
Reviewed By & Date | QA Head – 22-08-2012
Approved By & Date | MR – 23-08-2012
Actual Completion Date | 23-08-2012
Part E – Verification of Effectiveness
Description | Y/N | Evidence | Remarks
Root Cause Analysis Addressed? | Y | Attached Evidence
Corrective Action Effective? | Y | Attached Evidence
Recurrence Prevention Effective? | Y | Attached Evidence
Documents Revised? | Y | Attached Evidence
Training Conducted? | Y | Attached Evidence
Training Effectiveness Verified? | Y | Attached Evidence
Customer Approval (if applicable)? | Y | Attached Evidence
Corrective Action Closed & Verified? | Y | Attached Evidence
Applicable Compliance Standards
ISO 9001:2015 | Clause 10.2 Nonconformity & Corrective Action
IATF 16949:2016 | Clause 10.2.6 Automotive
ISO 13485:2016 | Medical Devices
AS9100D | Aerospace Standard
ISO 14001:2015 & ISO 45001:2018 | Environment & Occupational Health/Safety

## Disclaimer
Any articles, templates, or information provided by inpaspages.com on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.