## Sheet1
Risk management Plan
| Ravalian Aero Ind. |  |  | Project name : Welding (S.S.) |  | Plan No. : RMP/2012/3 |  | R.M. Date : 17/04/2012
| C-55, GT Road, Local Circle, Opp. Super man market, TX, USA |  |  | Plan scope : R.M ¦ Maintenance ¦ Planning
Define the risk management methodology
The risk management process is scalable to ensure that the level, type, and visibility of risk management are commensurate with both the risk and the importance of the project.
|  | Risk Identifcation | Risk Assessment Questionnaire |  |  | Risk Impact Assessment | Assess the risk event in terms of likelihood of occurrence and its effect on project objectives if the risk event occurs
|  | Categorize Risks | Groups the risks into categories |  |  | Prioritize Risks | Risks that meet the threshold criteria will be recorded in the Risk Response Plan
|  | Risk Response Planning | Determine the options and actions to reduce the likelihood or consequences of impact to the project’s objectives |  |  | Risk Response Tracking | Document the dates and the actions taken to mitigate the risk.
|  | Monitor Risk | Establish systematic reviews and schedule them in the project schedule. |  |  | Control Risk | Revise the Risk Assessment Questionnaire and other risk management documents to capture results of mitigation actions
|  | Define assumptions that have a significant impact on project risk |  |  |  | Define risk rating/scoring techniques
The project will rate each identified risk (High, Medium, Low) based on the likelihood that the risk event will occur and the effect on objectives if the risk event occurs.
|  | Define the roles and responsibilities unique to the Risk Management function |  |  |  | Establish risk thresholds
The project will establish risk responses for risk events that have been determined to have a rating of “High”.
|  | Define Risk Management Milestones |  |  |  | Define risk communications
|  | Milestone |  |  | Date | ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________
Risk Management Plan approved
|  | Risk Assessment Questionnaire tailored to project |  |  |  | Define risk tracking process
|  | Risk Assessment Questionnaire complete |  |  |  | ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________
Risk Response Plan approved
Risk Management Reviews scheduled

A
B
C
D
E
F
G
H








## Disclaimer
Any articles, templates, or information provided by inpaspages.com on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.